## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 02. Doctor Search | 02.01 | Search by Specialty | Design search by specialty UI wireframe and layout | N | 2026-03-25 | 2026-03-26 | 100% | Yukta Chaubal
2 | 02. Doctor Search | 02.01 | Search by Specialty | Implement GUI components for specialty search page | Y | 2026-03-25 | 2026-03-26 | 100% | Sreenidhi Madireddy
3 | 02. Doctor Search | 02.01 | Search by Specialty | Build API endpoint for specialty-based doctor search | Y | 2026-03-25 | 2026-03-26 | 100% | Priya Angel Dasari
4 | 02. Doctor Search | 02.01 | Search by Specialty | Implement core search logic with specialty filtering | N | 2026-03-25 | 2026-03-26 | 100% | Chalukya Garikapati
5 | 02. Doctor Search | 02.01 | Search by Specialty | Implement field validation for specialty search input | N | 2026-03-25 | 2026-03-26 | 100% | Sai Kumar
6 | 02. Doctor Search | 02.01 | Search by Specialty | Enrich search results with doctor profile summary data | N | 2026-03-25 | 2026-03-26 | 100% | Abhinay Reddy
7 | 02. Doctor Search | 02.01 | Search by Specialty | Implement role-based access control for search feature | N | 2026-03-25 | 2026-03-26 | 100% | Karishma Avhad
8 | 02. Doctor Search | 02.01 | Search by Specialty | Implement caching for frequently searched specialties | N | 2026-03-25 | 2026-03-26 | 100% | Jinali
9 | 02. Doctor Search | 02.01 | Search by Specialty | Optimize search query performance for large datasets | N | 2026-03-25 | 2026-03-26 | 100% | Bansri Patel
10 | 02. Doctor Search | 02.01 | Search by Specialty | Implement error handling and logging for search failures | N | 2026-03-25 | 2026-03-26 | 100% | Raghava Thyagaraj
11 | 02. Doctor Search | 02.01 | Search by Specialty | Verify specialty search returns accurate filtered results | N | 2026-03-25 | 2026-03-26 | 100% | Jinali
12 | 02. Doctor Search | 02.01 | Search by Specialty | Perform exploratory testing on search functionality | N | 2026-03-25 | 2026-03-26 | 100% | Karishma Avhad
13 | 02. Doctor Search | 02.02 | Search by Location | Design search by location UI layout | N | 2026-03-27 | 2026-03-28 | 100% | Yukta Chaubal
14 | 02. Doctor Search | 02.02 | Search by Location | Implement GUI components for location-based search | N | 2026-03-27 | 2026-03-28 | 100% | Chalukya Garikapati
15 | 02. Doctor Search | 02.02 | Search by Location | Build API endpoint for location-based doctor search | Y | 2026-03-27 | 2026-03-28 | 100% | Raghava Thyagaraj
16 | 02. Doctor Search | 02.02 | Search by Location | Implement core search logic with location filtering | N | 2026-03-27 | 2026-03-28 | 100% | Abhinay Reddy
17 | 02. Doctor Search | 02.02 | Search by Location | Implement field validation for location input fields | N | 2026-03-27 | 2026-03-28 | 100% | Karishma Avhad
18 | 02. Doctor Search | 02.02 | Search by Location | Enrich search results with distance and availability data | N | 2026-03-27 | 2026-03-28 | 100% | Jinali
19 | 02. Doctor Search | 02.02 | Search by Location | Implement caching for location-based search results | N | 2026-03-27 | 2026-03-28 | 100% | Bansri Patel
20 | 02. Doctor Search | 02.02 | Search by Location | Optimize location search query performance | N | 2026-03-27 | 2026-03-28 | 100% | Priya Angel Dasari
21 | 02. Doctor Search | 02.02 | Search by Location | Implement error handling for invalid location inputs | N | 2026-03-27 | 2026-03-28 | 100% | Sreenidhi Madireddy
22 | 02. Doctor Search | 02.02 | Search by Location | Verify location search returns geographically accurate results | N | 2026-03-27 | 2026-03-28 | 100% | Karishma Avhad
23 | 02. Doctor Search | 02.02 | Search by Location | Perform exploratory testing on location search | N | 2026-03-27 | 2026-03-28 | 100% | Jinali
24 | 02. Doctor Search | 02.03 | Search by Name | Design search by name UI with autocomplete suggestions | N | 2026-03-29 | 2026-03-30 | 100% | Yukta Chaubal
25 | 02. Doctor Search | 02.03 | Search by Name | Implement GUI for name search with real-time suggestions | N | 2026-03-29 | 2026-03-30 | 100% | Chalukya Garikapati
26 | 02. Doctor Search | 02.03 | Search by Name | Build API endpoint for name-based doctor search | Y | 2026-03-29 | 2026-03-30 | 100% | Sai Kumar
27 | 02. Doctor Search | 02.03 | Search by Name | Implement core search logic with partial name matching | N | 2026-03-29 | 2026-03-30 | 100% | Abhinay Reddy
28 | 02. Doctor Search | 02.03 | Search by Name | Implement field validation for name search input | N | 2026-03-29 | 2026-03-30 | 100% | Karishma Avhad
29 | 02. Doctor Search | 02.03 | Search by Name | Enrich search results with doctor specialty and ratings | N | 2026-03-29 | 2026-03-30 | 100% | Jinali
30 | 02. Doctor Search | 02.03 | Search by Name | Implement caching for name search results | N | 2026-03-29 | 2026-03-30 | 100% | Bansri Patel
31 | 02. Doctor Search | 02.03 | Search by Name | Implement error handling for empty search results | N | 2026-03-29 | 2026-03-30 | 100% | Raghava Thyagaraj
32 | 02. Doctor Search | 02.03 | Search by Name | Verify name search handles special characters and edge cases | N | 2026-03-29 | 2026-03-30 | 100% | Yukta Chaubal
33 | 02. Doctor Search | 02.03 | Search by Name | Perform exploratory testing on name search functionality | N | 2026-03-29 | 2026-03-30 | 100% | Yukta Chaubal
34 | 02. Doctor Search | 02.04 | Add to Favorites | Design favorites UI with add/remove toggle button | N | 2026-03-29 | 2026-03-30 | 100% | Chalukya Garikapati
35 | 02. Doctor Search | 02.04 | Add to Favorites | Implement GUI for favorites list display and management | Y | 2026-03-29 | 2026-03-30 | 100% | Sai Kumar
36 | 02. Doctor Search | 02.04 | Add to Favorites | Build API endpoints for adding and removing favorites | N | 2026-03-29 | 2026-03-30 | 100% | Abhinay Reddy
37 | 02. Doctor Search | 02.04 | Add to Favorites | Implement core favorites logic with user profile dependency | N | 2026-03-29 | 2026-03-30 | 100% | Karishma Avhad
38 | 02. Doctor Search | 02.04 | Add to Favorites | Implement data flow in to retrieve existing favorites list | N | 2026-03-29 | 2026-03-30 | 100% | Jinali
39 | 02. Doctor Search | 02.04 | Add to Favorites | Implement data flow out to persist favorites changes | N | 2026-03-29 | 2026-03-30 | 100% | Bansri Patel
40 | 02. Doctor Search | 02.04 | Add to Favorites | Implement audit trail logging for favorites modifications | N | 2026-03-29 | 2026-03-30 | 100% | Sreenidhi Madireddy
41 | 02. Doctor Search | 02.04 | Add to Favorites | Implement caching for favorites list retrieval | N | 2026-03-29 | 2026-03-30 | 100% | Priya Angel Dasari
42 | 02. Doctor Search | 02.04 | Add to Favorites | Implement error handling for favorites operations | N | 2026-03-29 | 2026-03-30 | 100% | Raghava Thyagaraj
43 | 02. Doctor Search | 02.04 | Add to Favorites | Verify favorites persist correctly across user sessions | N | 2026-03-29 | 2026-03-30 | 100% | Karishma Avhad
44 | 02. Doctor Search | 02.04 | Add to Favorites | Perform exploratory testing on favorites functionality | N | 2026-03-29 | 2026-03-30 | 100% | Jinali
45 | 02. Doctor Search | 02.06 | View Doctor Profile | Design doctor profile page layout and UI components | N | 2026-04-07 | 2026-04-08 | 100% | Bansri Patel
46 | 02. Doctor Search | 02.06 | View Doctor Profile | Implement GUI for displaying doctor profile details | Y | 2026-04-08 | 2026-04-10 | 100% | Raghava Thyagaraj
47 | 02. Doctor Search | 02.06 | View Doctor Profile | Build API endpoint for fetching doctor profile data | N | 2026-04-08 | 2026-04-10 | 100% | Bansri Patel
48 | 02. Doctor Search | 02.06 | View Doctor Profile | Implement core profile display logic with specialty info | N | 2026-04-09 | 2026-04-11 | 100% | Raghava Thyagaraj
49 | 02. Doctor Search | 02.06 | View Doctor Profile | Implement data flow in to retrieve doctor details and reviews | N | 2026-04-09 | 2026-04-11 | 100% | Yukta Chaubal
50 | 02. Doctor Search | 02.06 | View Doctor Profile | Enrich profile page with ratings, reviews, and availability | N | 2026-04-10 | 2026-04-12 | 100% | Yukta Chaubal
51 | 02. Doctor Search | 02.06 | View Doctor Profile | Implement caching for doctor profile data | N | 2026-04-11 | 2026-04-12 | 100% | Chalukya Garikapati
52 | 02. Doctor Search | 02.06 | View Doctor Profile | Optimize profile page load performance | N | 2026-04-11 | 2026-04-13 | 100% | Sai Kumar
53 | 02. Doctor Search | 02.06 | View Doctor Profile | Implement error handling for missing or incomplete profiles | N | 2026-04-11 | 2026-04-12 | 100% | Abhinay Reddy
54 | 02. Doctor Search | 02.06 | View Doctor Profile | Verify doctor profile displays all required information accurately | N | 2026-04-14 | 2026-04-15 | 100% | Karishma Avhad
55 | 02. Doctor Search | 02.06 | View Doctor Profile | Perform exploratory testing on profile page | N | 2026-04-15 | 2026-04-16 | 100% | Jinali
56 | 04. Provider Management | 04.01 | Add Doctor Profile | Design doctor profile creation form UI | N | 2026-04-11 | 2026-04-12 | 100% | Bansri Patel
57 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement GUI for doctor profile creation with specialty selection | Y | 2026-04-12 | 2026-04-14 | 100% | Sreenidhi Madireddy
58 | 04. Provider Management | 04.01 | Add Doctor Profile | Build API endpoint for creating new doctor profiles | Y | 2026-04-12 | 2026-04-14 | 100% | Priya Angel Dasari
59 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement core profile creation logic with client setup dependency | N | 2026-04-12 | 2026-04-15 | 100% | Raghava Thyagaraj
60 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement field validation for doctor registration fields | N | 2026-04-13 | 2026-04-14 | 100% | Karishma Avhad
61 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement doctor specialty selection and validation | N | 2026-04-13 | 2026-04-14 | 100% | Raghava Thyagaraj
62 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement data flow out to store new doctor profile | N | 2026-04-13 | 2026-04-15 | 100% | Yukta Chaubal
63 | 04. Provider Management | 04.01 | Add Doctor Profile | Enrich profile with default values from specialty data | N | 2026-04-14 | 2026-04-15 | 100% | Yukta Chaubal
64 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement audit trail for doctor profile creation | N | 2026-04-14 | 2026-04-15 | 100% | Chalukya Garikapati
65 | 04. Provider Management | 04.01 | Add Doctor Profile | Implement error handling for profile creation failures | N | 2026-04-14 | 2026-04-15 | 100% | Sai Kumar
66 | 04. Provider Management | 04.01 | Add Doctor Profile | Verify doctor profile creation stores all fields correctly | N | 2026-04-16 | 2026-04-17 | 100% | Abhinay Reddy
67 | 04. Provider Management | 04.01 | Add Doctor Profile | Perform exploratory testing on doctor profile creation | N | 2026-04-17 | 2026-04-18 | 100% | Karishma Avhad
68 | 04. Provider Management | 04.02 | Update Schedule | Design schedule management UI with calendar view | N | 2026-04-11 | 2026-04-12 | 100% | Jinali
69 | 04. Provider Management | 04.02 | Update Schedule | Implement GUI for schedule editing with time slot management | Y | 2026-04-12 | 2026-04-15 | 100% | Bansri Patel
70 | 04. Provider Management | 04.02 | Update Schedule | Build API endpoints for schedule CRUD operations | Y | 2026-04-12 | 2026-04-15 | 100% | Sreenidhi Madireddy
71 | 04. Provider Management | 04.02 | Update Schedule | Implement core schedule update logic with availability rules | N | 2026-04-12 | 2026-04-15 | 100% | Priya Angel Dasari
72 | 04. Provider Management | 04.02 | Update Schedule | Implement field validation for schedule time inputs | N | 2026-04-13 | 2026-04-14 | 100% | Raghava Thyagaraj
73 | 04. Provider Management | 04.02 | Update Schedule | Implement data-dependency validation for overlapping time slots | N | 2026-04-13 | 2026-04-15 | 100% | Karishma Avhad
74 | 04. Provider Management | 04.02 | Update Schedule | Implement data-driven defaults for recurring schedule patterns | N | 2026-04-14 | 2026-04-15 | 100% | Chalukya Garikapati
75 | 04. Provider Management | 04.02 | Update Schedule | Implement appointment status check before schedule modification | N | 2026-04-14 | 2026-04-15 | 100% | Sai Kumar
76 | 04. Provider Management | 04.02 | Update Schedule | Implement concurrency control for simultaneous schedule edits | N | 2026-04-14 | 2026-04-16 | 100% | Abhinay Reddy
77 | 04. Provider Management | 04.02 | Update Schedule | Implement timezone handling for schedule display and storage | N | 2026-04-14 | 2026-04-15 | 100% | Karishma Avhad
78 | 04. Provider Management | 04.02 | Update Schedule | Implement data flow in to retrieve existing schedule data | N | 2026-04-13 | 2026-04-14 | 100% | Jinali
79 | 04. Provider Management | 04.02 | Update Schedule | Implement data flow out to persist schedule changes | N | 2026-04-14 | 2026-04-15 | 100% | Bansri Patel
80 | 04. Provider Management | 04.02 | Update Schedule | Implement audit trail for schedule modifications | N | 2026-04-15 | 2026-04-16 | 100% | Sreenidhi Madireddy
81 | 04. Provider Management | 04.02 | Update Schedule | Implement caching for schedule display optimization | N | 2026-04-15 | 2026-04-16 | 100% | Priya Angel Dasari
82 | 04. Provider Management | 04.02 | Update Schedule | Implement error handling for schedule update failures | N | 2026-04-15 | 2026-04-16 | 100% | Raghava Thyagaraj
83 | 04. Provider Management | 04.02 | Update Schedule | Verify schedule updates reflect correctly across all views | N | 2026-04-17 | 2026-04-18 | 100% | Karishma Avhad
84 | 04. Provider Management | 04.02 | Update Schedule | Validate concurrent schedule editing does not cause conflicts | N | 2026-04-17 | 2026-04-18 | 100% | Chalukya Garikapati
85 | 04. Provider Management | 04.02 | Update Schedule | Perform exploratory testing on schedule management | N | 2026-04-18 | 2026-04-19 | 100% | Sai Kumar
86 | 05. Reviews & Ratings | 05.03 | View Reviews | Design reviews display UI with rating summary | N | 2026-04-14 | 2026-04-15 | 100% | Abhinay Reddy
87 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement GUI for displaying reviews list with pagination | Y | 2026-04-15 | 2026-04-17 | 100% | Karishma Avhad
88 | 05. Reviews & Ratings | 05.03 | View Reviews | Build API endpoint for fetching reviews by doctor | N | 2026-04-15 | 2026-04-17 | 100% | Jinali
89 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement core review display logic with specialty context | N | 2026-04-15 | 2026-04-17 | 100% | Bansri Patel
90 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement data flow in to retrieve review and rating data | N | 2026-04-16 | 2026-04-17 | 100% | Sreenidhi Madireddy
91 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement data flow out to track review views for analytics | N | 2026-04-16 | 2026-04-17 | 100% | Priya Angel Dasari
92 | 05. Reviews & Ratings | 05.03 | View Reviews | Enrich reviews display with reviewer profile information | N | 2026-04-16 | 2026-04-17 | 100% | Raghava Thyagaraj
93 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement caching for reviews page performance | N | 2026-04-17 | 2026-04-18 | 100% | Karishma Avhad
94 | 05. Reviews & Ratings | 05.03 | View Reviews | Optimize review loading performance for large review sets | N | 2026-04-17 | 2026-04-18 | 100% | Bansri Patel
95 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement error handling for review retrieval failures | N | 2026-04-17 | 2026-04-18 | 100% | Sreenidhi Madireddy
96 | 05. Reviews & Ratings | 05.03 | View Reviews | Verify reviews display correctly with accurate rating calculations | N | 2026-04-18 | 2026-04-19 | 100% | Priya Angel Dasari
97 | 05. Reviews & Ratings | 05.03 | View Reviews | Perform exploratory testing on reviews functionality | N | 2026-04-19 | 2026-04-20 | 100% | Bansri Patel

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 03. Appointment Booking | 03.01 | View Available Slots | Design slot availability calendar UI wireframe and layout | N | 2026-04-29 | 2026-04-30 | 100% | Yukta Chaubal
2 | 03. Appointment Booking | 03.01 | View Available Slots | Implement GUI components for slot availability grid | Y | 2026-04-29 | 2026-04-30 | 100% | Sreenidhi Madireddy
3 | 03. Appointment Booking | 03.01 | View Available Slots | Build API endpoint for fetching doctor available slots | Y | 2026-04-29 | 2026-04-30 | 100% | Priya Angel Dasari
4 | 03. Appointment Booking | 03.01 | View Available Slots | Implement core availability logic with appointment status filter | N | 2026-04-29 | 2026-04-30 | 100% | Chalukya Garikapati
5 | 03. Appointment Booking | 03.01 | View Available Slots | Implement doctor specialty slot duration defaults | N | 2026-04-30 | 2026-05-01 | 100% | Sai Kumar
6 | 03. Appointment Booking | 03.01 | View Available Slots | Implement data-dependency validation for blocked dates and working hours | N | 2026-04-30 | 2026-05-01 | 100% | Abhinay Reddy
7 | 03. Appointment Booking | 03.01 | View Available Slots | Implement timezone conversion for slot display in patient local time | N | 2026-04-30 | 2026-05-01 | 100% | Karishma Avhad
8 | 03. Appointment Booking | 03.01 | View Available Slots | Implement concurrency control for real-time slot availability | N | 2026-05-01 | 2026-05-04 | 100% | Jinali Parekh
9 | 03. Appointment Booking | 03.01 | View Available Slots | Implement caching for doctor schedule and availability data | N | 2026-05-01 | 2026-05-04 | 100% | Bansri Patel
10 | 03. Appointment Booking | 03.01 | View Available Slots | Implement audit trail logging for slot view events | N | 2026-05-04 | 2026-05-05 | 100% | Raghava Thyagaraj
11 | 03. Appointment Booking | 03.01 | View Available Slots | Implement error handling for DB failures during slot load | N | 2026-05-04 | 2026-05-05 | 100% | Priya Angel Dasari
12 | 03. Appointment Booking | 03.01 | View Available Slots | Produce Test Design Specification | N | 2026-05-05 | 2026-05-08 | 100% | Yukta Chaubal
13 | 03. Appointment Booking | 03.01 | View Available Slots | Produce Test Case Specification | N | 2026-05-05 | 2026-05-08 | 100% | Yukta Chaubal
14 | 03. Appointment Booking | 03.01 | View Available Slots | Verify slot grid accurately reflects real-time availability | N | 2026-05-05 | 2026-05-06 | 100% | Karishma Avhad
15 | 03. Appointment Booking | 03.01 | View Available Slots | Perform exploratory testing on slot availability page | N | 2026-05-06 | 2026-05-07 | 100% | Jinali Parekh
16 | 03. Appointment Booking | 03.02 | Book Appointment | Design appointment booking form UI and confirmation page | N | 2026-04-29 | 2026-04-30 | 100% | Yukta Chaubal
17 | 03. Appointment Booking | 03.02 | Book Appointment | Implement GUI components for booking form and summary page | Y | 2026-04-29 | 2026-04-30 | 100% | Raghava Thyagaraj
18 | 03. Appointment Booking | 03.02 | Book Appointment | Build API endpoint for appointment creation | Y | 2026-04-29 | 2026-04-30 | 100% | Sreenidhi Madireddy
19 | 03. Appointment Booking | 03.02 | Book Appointment | Implement core booking logic with slot reservation and status management | N | 2026-04-29 | 2026-05-01 | 100% | Chalukya Garikapati
20 | 03. Appointment Booking | 03.02 | Book Appointment | Implement field validation for booking form inputs | N | 2026-04-30 | 2026-05-01 | 100% | Sai Kumar
21 | 03. Appointment Booking | 03.02 | Book Appointment | Implement data-dependency validation to prevent double booking | N | 2026-04-30 | 2026-05-01 | 100% | Abhinay Reddy
22 | 03. Appointment Booking | 03.02 | Book Appointment | Implement data-driven defaults for patient profile pre-fill | N | 2026-05-01 | 2026-05-04 | 100% | Karishma Avhad
23 | 03. Appointment Booking | 03.02 | Book Appointment | Implement payment status tracking linked to appointment record | N | 2026-05-01 | 2026-05-04 | 100% | Priya Angel Dasari
24 | 03. Appointment Booking | 03.02 | Book Appointment | Implement timezone handling for appointment datetime storage | N | 2026-05-01 | 2026-05-04 | 100% | Bansri Patel
25 | 03. Appointment Booking | 03.02 | Book Appointment | Implement outbound system interface for booking confirmation email and SMS | Y | 2026-05-04 | 2026-05-05 | 100% | Sreenidhi Madireddy
26 | 03. Appointment Booking | 03.02 | Book Appointment | Implement audit trail for booking creation and payment events | N | 2026-05-04 | 2026-05-05 | 100% | Raghava Thyagaraj
27 | 03. Appointment Booking | 03.02 | Book Appointment | Implement error handling for payment failures and slot conflicts | N | 2026-05-05 | 2026-05-06 | 100% | Priya Angel Dasari
28 | 03. Appointment Booking | 03.02 | Book Appointment | Produce Test Design Specification | N | 2026-05-06 | 2026-05-09 | 100% | Yukta Chaubal
29 | 03. Appointment Booking | 03.02 | Book Appointment | Produce Test Case Specification | N | 2026-05-06 | 2026-05-09 | 100% | Yukta Chaubal
30 | 03. Appointment Booking | 03.02 | Book Appointment | Verify booking creates correct appointment and payment records | N | 2026-05-06 | 2026-05-07 | 100% | Sai Kumar
31 | 03. Appointment Booking | 03.02 | Book Appointment | Perform exploratory testing on end-to-end booking flow | N | 2026-05-07 | 2026-05-08 | 100% | Jinali Parekh
32 | 03. Appointment Booking | 03.03 | Reschedule Booking | Design reschedule UI showing old vs new slot comparison | N | 2026-04-30 | 2026-05-01 | 100% | Yukta Chaubal
33 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement GUI components for reschedule flow | Y | 2026-04-30 | 2026-05-01 | 100% | Chalukya Garikapati
34 | 03. Appointment Booking | 03.03 | Reschedule Booking | Build API endpoint for reschedule with atomic slot swap | Y | 2026-04-30 | 2026-05-01 | 100% | Raghava Thyagaraj
35 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement core reschedule logic with appointment status validation | N | 2026-05-01 | 2026-05-04 | 100% | Sai Kumar
36 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement field validation for new date and slot selection | N | 2026-05-01 | 2026-05-04 | 100% | Abhinay Reddy
37 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement data-dependency validation for cancellation policy window | N | 2026-05-01 | 2026-05-04 | 100% | Karishma Avhad
38 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement concurrency control for atomic old/new slot swap | N | 2026-05-04 | 2026-05-05 | 100% | Priya Angel Dasari
39 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement timezone handling for rescheduled appointment display | N | 2026-05-04 | 2026-05-05 | 100% | Bansri Patel
40 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement outbound notification for reschedule confirmation | Y | 2026-05-05 | 2026-05-06 | 100% | Sreenidhi Madireddy
41 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement audit trail for reschedule action with old and new slot | N | 2026-05-05 | 2026-05-06 | 100% | Raghava Thyagaraj
42 | 03. Appointment Booking | 03.03 | Reschedule Booking | Implement error handling for slot conflicts and policy violations | N | 2026-05-06 | 2026-05-07 | 100% | Priya Angel Dasari
43 | 03. Appointment Booking | 03.03 | Reschedule Booking | Produce Test Design Specification | N | 2026-05-07 | 2026-05-09 | 100% | Yukta Chaubal
44 | 03. Appointment Booking | 03.03 | Reschedule Booking | Produce Test Case Specification | N | 2026-05-07 | 2026-05-09 | 100% | Yukta Chaubal
45 | 03. Appointment Booking | 03.03 | Reschedule Booking | Verify reschedule correctly swaps slots and notifies doctor | N | 2026-05-07 | 2026-05-08 | 100% | Karishma Avhad
46 | 03. Appointment Booking | 03.03 | Reschedule Booking | Perform exploratory testing on reschedule flow | N | 2026-05-08 | 2026-05-09 | 100% | Jinali Parekh
47 | 03. Appointment Booking | 03.04 | Cancel Booking | Design cancellation UI with policy warning and confirmation modal | N | 2026-04-30 | 2026-05-01 | 100% | Yukta Chaubal
48 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement GUI for cancel flow with two-step confirmation | Y | 2026-04-30 | 2026-05-01 | 100% | Chalukya Garikapati
49 | 03. Appointment Booking | 03.04 | Cancel Booking | Build API endpoint for appointment cancellation and refund trigger | Y | 2026-05-01 | 2026-05-04 | 100% | Raghava Thyagaraj
50 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement core cancellation logic with status transition | N | 2026-05-01 | 2026-05-04 | 100% | Sai Kumar
51 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement data-dependency validation for cancellation policy window | N | 2026-05-01 | 2026-05-04 | 100% | Abhinay Reddy
52 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement payment status update and refund eligibility logic | N | 2026-05-04 | 2026-05-05 | 100% | Priya Angel Dasari
53 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement concurrency control to prevent cancel during In-Progress | N | 2026-05-04 | 2026-05-05 | 100% | Karishma Avhad
54 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement timezone-aware cancellation policy deadline display | N | 2026-05-04 | 2026-05-05 | 100% | Bansri Patel
55 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement outbound notifications for cancellation confirmation to patient and doctor | Y | 2026-05-05 | 2026-05-06 | 100% | Sreenidhi Madireddy
56 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement audit trail for cancellation with refund decision logged | N | 2026-05-05 | 2026-05-06 | 100% | Raghava Thyagaraj
57 | 03. Appointment Booking | 03.04 | Cancel Booking | Implement error handling for Stripe refund failures and policy violations | N | 2026-05-06 | 2026-05-07 | 100% | Priya Angel Dasari
58 | 03. Appointment Booking | 03.04 | Cancel Booking | Produce Test Design Specification | N | 2026-05-07 | 2026-05-10 | 100% | Yukta Chaubal
59 | 03. Appointment Booking | 03.04 | Cancel Booking | Produce Test Case Specification | N | 2026-05-07 | 2026-05-10 | 100% | Yukta Chaubal
60 | 03. Appointment Booking | 03.04 | Cancel Booking | Verify cancellation updates slot availability and triggers correct refund | N | 2026-05-07 | 2026-05-08 | 100% | Karishma Avhad
61 | 03. Appointment Booking | 03.04 | Cancel Booking | Perform exploratory testing on cancellation and refund scenarios | N | 2026-05-08 | 2026-05-09 | 100% | Jinali Parekh
62 | 03. Appointment Booking | 03.05 | View Booking History | Design My Appointments page layout with status badges and filters | N | 2026-04-30 | 2026-05-01 | 100% | Yukta Chaubal
63 | 03. Appointment Booking | 03.05 | View Booking History | Implement GUI for appointments list with pagination and filter controls | Y | 2026-05-01 | 2026-05-04 | 100% | Chalukya Garikapati
64 | 03. Appointment Booking | 03.05 | View Booking History | Build API endpoint for fetching patient appointment history | Y | 2026-05-01 | 2026-05-04 | 100% | Raghava Thyagaraj
65 | 03. Appointment Booking | 03.05 | View Booking History | Implement core history display logic with all 7 appointment statuses | N | 2026-05-01 | 2026-05-04 | 100% | Sai Kumar
66 | 03. Appointment Booking | 03.05 | View Booking History | Implement timezone conversion for all appointment datetime display | N | 2026-05-04 | 2026-05-05 | 100% | Bansri Patel
67 | 03. Appointment Booking | 03.05 | View Booking History | Implement data flow in to join appointment, doctor and payment records | N | 2026-05-04 | 2026-05-05 | 100% | Abhinay Reddy
68 | 03. Appointment Booking | 03.05 | View Booking History | Implement data flow out linking Reschedule, Cancel and Write Review actions | N | 2026-05-05 | 2026-05-06 | 100% | Karishma Avhad
69 | 03. Appointment Booking | 03.05 | View Booking History | Implement caching for booking history with per-patient TTL | N | 2026-05-05 | 2026-05-06 | 100% | Bansri Patel
70 | 03. Appointment Booking | 03.05 | View Booking History | Implement error handling for DB failures and missing join data | N | 2026-05-06 | 2026-05-07 | 100% | Priya Angel Dasari
71 | 03. Appointment Booking | 03.05 | View Booking History | Produce Test Design Specification | N | 2026-05-07 | 2026-05-10 | 100% | Chalukya Garikapati
72 | 03. Appointment Booking | 03.05 | View Booking History | Produce Test Case Specification | N | 2026-05-07 | 2026-05-10 | 100% | Chalukya Garikapati
73 | 03. Appointment Booking | 03.05 | View Booking History | Verify booking history shows accurate statuses across all appointment types | N | 2026-05-07 | 2026-05-08 | 100% | Karishma Avhad
74 | 03. Appointment Booking | 03.05 | View Booking History | Perform exploratory testing on booking history filtering and pagination | N | 2026-05-08 | 2026-05-09 | 100% | Jinali Parekh
75 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Design reminder preferences UI for patient email/SMS toggle | N | 2026-05-01 | 2026-05-04 | 100% | Yukta Chaubal
76 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement background scheduler for automated 24-hour and 1-hour reminders | Y | 2026-05-01 | 2026-05-04 | 100% | Raghava Thyagaraj
77 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement outbound SendGrid email and Twilio SMS reminder dispatch | Y | 2026-05-04 | 2026-05-05 | 100% | Sreenidhi Madireddy
78 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement appointment status filter to suppress non-Confirmed reminders | N | 2026-05-04 | 2026-05-05 | 100% | Sai Kumar
79 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement external entitlements for SendGrid and Twilio API authentication | N | 2026-05-04 | 2026-05-05 | 100% | Abhinay Reddy
80 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement timezone-aware reminder send window per patient local time | N | 2026-05-05 | 2026-05-06 | 100% | Bansri Patel
81 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement data flow out to reminder_log for dispatch tracking | N | 2026-05-05 | 2026-05-06 | 100% | Karishma Avhad
82 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Implement error handling and retry logic for failed reminder dispatches | N | 2026-05-06 | 2026-05-07 | 100% | Priya Angel Dasari
83 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Produce Test Design Specification | N | 2026-05-08 | 2026-05-11 | 100% | Chalukya Garikapati
84 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Produce Test Case Specification | N | 2026-05-08 | 2026-05-11 | 100% | Chalukya Garikapati
85 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Verify reminders sent at correct times in patient timezone | N | 2026-05-07 | 2026-05-08 | 100% | Jinali Parekh
86 | 03. Appointment Booking | 03.06 | Send Booking Reminder | Perform exploratory testing on reminder scheduler and API dispatch | N | 2026-05-08 | 2026-05-09 | 100% | Chalukya Garikapati
87 | 04. Provider Management | 04.03 | Manage Availability | Design availability management calendar UI with working hours editor | N | 2026-04-29 | 2026-04-30 | 100% | Yukta Chaubal
88 | 04. Provider Management | 04.03 | Manage Availability | Implement GUI for weekly calendar availability editor with block dates | Y | 2026-04-29 | 2026-04-30 | 100% | Chalukya Garikapati
89 | 04. Provider Management | 04.03 | Manage Availability | Build API endpoints for doctor schedule CRUD operations | Y | 2026-04-29 | 2026-04-30 | 100% | Raghava Thyagaraj
90 | 04. Provider Management | 04.03 | Manage Availability | Implement core availability management logic with specialty slot duration | N | 2026-04-30 | 2026-05-01 | 100% | Sai Kumar
91 | 04. Provider Management | 04.03 | Manage Availability | Implement field validation for working hours and date range inputs | N | 2026-04-30 | 2026-05-01 | 100% | Abhinay Reddy
92 | 04. Provider Management | 04.03 | Manage Availability | Implement data-dependency validation to block removal of slots with bookings | N | 2026-05-01 | 2026-05-04 | 100% | Karishma Avhad
93 | 04. Provider Management | 04.03 | Manage Availability | Implement data-driven defaults for specialty-based schedule setup | N | 2026-05-01 | 2026-05-04 | 100% | Bansri Patel
94 | 04. Provider Management | 04.03 | Manage Availability | Implement concurrency control for simultaneous booking and availability edit | N | 2026-05-01 | 2026-05-04 | 100% | Priya Angel Dasari
95 | 04. Provider Management | 04.03 | Manage Availability | Implement timezone handling for doctor schedule storage and patient slot display | N | 2026-05-04 | 2026-05-05 | 100% | Bansri Patel
96 | 04. Provider Management | 04.03 | Manage Availability | Implement data flow out to invalidate slot availability cache on save | N | 2026-05-04 | 2026-05-05 | 100% | Sreenidhi Madireddy
97 | 04. Provider Management | 04.03 | Manage Availability | Implement caching for doctor schedule with TTL and save-time invalidation | N | 2026-05-05 | 2026-05-06 | 100% | Jinali Parekh
98 | 04. Provider Management | 04.03 | Manage Availability | Implement audit trail for all availability changes with before/after state | N | 2026-05-05 | 2026-05-06 | 100% | Raghava Thyagaraj
99 | 04. Provider Management | 04.03 | Manage Availability | Implement error handling for conflict detection and DB save failures | N | 2026-05-06 | 2026-05-07 | 100% | Priya Angel Dasari
100 | 04. Provider Management | 04.03 | Manage Availability | Produce Test Design Specification | N | 2026-05-08 | 2026-05-11 | 100% | Sai Kumar
101 | 04. Provider Management | 04.03 | Manage Availability | Produce Test Case Specification | N | 2026-05-08 | 2026-05-11 | 100% | Sai Kumar
102 | 04. Provider Management | 04.03 | Manage Availability | Verify availability changes immediately reflect in patient slot view | N | 2026-05-07 | 2026-05-08 | 100% | Karishma Avhad
103 | 04. Provider Management | 04.03 | Manage Availability | Perform exploratory testing on availability management and conflict scenarios | N | 2026-05-08 | 2026-05-09 | 100% | Jinali Parekh
104 | 05. Reviews & Ratings | 05.01 | Submit Review | Design review submission form UI with star rating and text input | N | 2026-05-01 | 2026-05-04 | 100% | Yukta Chaubal
105 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement GUI for review form with character counter and rating selector | Y | 2026-05-01 | 2026-05-04 | 100% | Chalukya Garikapati
106 | 05. Reviews & Ratings | 05.01 | Submit Review | Build API endpoint for review submission with duplicate check | Y | 2026-05-01 | 2026-05-04 | 100% | Raghava Thyagaraj
107 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement core review submission logic with appointment ownership validation | N | 2026-05-04 | 2026-05-05 | 100% | Sai Kumar
108 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement field validation for review text length, rating and content rules | N | 2026-05-04 | 2026-05-05 | 100% | Abhinay Reddy
109 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement data-dependency validation to restrict reviews to Completed appointments | N | 2026-05-04 | 2026-05-05 | 100% | Karishma Avhad
110 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement concurrency control to prevent duplicate review submission | N | 2026-05-05 | 2026-05-06 | 100% | Priya Angel Dasari
111 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement data flow out to update doctor average rating on review insert | N | 2026-05-05 | 2026-05-06 | 100% | Bansri Patel
112 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement audit trail logging for review submissions | N | 2026-05-06 | 2026-05-07 | 100% | Raghava Thyagaraj
113 | 05. Reviews & Ratings | 05.01 | Submit Review | Implement error handling for duplicate reviews and DB failures | N | 2026-05-06 | 2026-05-07 | 100% | Priya Angel Dasari
114 | 05. Reviews & Ratings | 05.01 | Submit Review | Produce Test Design Specification | N | 2026-05-08 | 2026-05-11 | 100% | Sai Kumar
115 | 05. Reviews & Ratings | 05.01 | Submit Review | Produce Test Case Specification | N | 2026-05-08 | 2026-05-11 | 100% | Sai Kumar
116 | 05. Reviews & Ratings | 05.01 | Submit Review | Verify review submission updates doctor rating and appears in View Reviews | N | 2026-05-07 | 2026-05-08 | 100% | Karishma Avhad
117 | 05. Reviews & Ratings | 05.01 | Submit Review | Perform exploratory testing on review submission and edge cases | N | 2026-05-08 | 2026-05-09 | 100% | Jinali Parekh
118 | 05. Reviews & Ratings | 05.03 | View Reviews | Design reviews display UI with rating summary and pagination | N | 2026-05-04 | 2026-05-05 | 100% | Yukta Chaubal
119 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement GUI for reviews list with rating distribution chart | Y | 2026-05-04 | 2026-05-05 | 100% | Chalukya Garikapati
120 | 05. Reviews & Ratings | 05.03 | View Reviews | Build API endpoint for fetching paginated doctor reviews | Y | 2026-05-04 | 2026-05-05 | 100% | Raghava Thyagaraj
121 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement core review display logic with specialty context | N | 2026-05-05 | 2026-05-06 | 100% | Sai Kumar
122 | 05. Reviews & Ratings | 05.03 | View Reviews | Enrich review cards with verified badge, reviewer name and doctor response | N | 2026-05-05 | 2026-05-06 | 100% | Abhinay Reddy
123 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement data flow in to load approved reviews with rating aggregation | N | 2026-05-06 | 2026-05-07 | 100% | Karishma Avhad
124 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement data flow out to surface average rating on doctor profile card | N | 2026-05-06 | 2026-05-07 | 100% | Bansri Patel
125 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement caching for reviews per doctor with new-review cache invalidation | N | 2026-05-07 | 2026-05-08 | 100% | Jinali Parekh
126 | 05. Reviews & Ratings | 05.03 | View Reviews | Implement error handling for DB failures with fallback to stored avg rating | N | 2026-05-07 | 2026-05-08 | 100% | Priya Angel Dasari
127 | 05. Reviews & Ratings | 05.03 | View Reviews | Produce Test Design Specification | N | 2026-05-09 | 2026-05-12 | 100% | Abhinay Reddy
128 | 05. Reviews & Ratings | 05.03 | View Reviews | Produce Test Case Specification | N | 2026-05-09 | 2026-05-12 | 100% | Abhinay Reddy
129 | 05. Reviews & Ratings | 05.03 | View Reviews | Verify reviews display accurately with correct rating averages | N | 2026-05-08 | 2026-05-09 | 100% | Karishma Avhad
130 | 05. Reviews & Ratings | 05.03 | View Reviews | Perform exploratory testing on reviews page and filter functionality | N | 2026-05-09 | 2026-05-11 | 100% | Jinali Parekh