## Sheet1
Team 4: Jenkins Implementation Planning and Progress Tracking
Admin: | Raghava Thyagaraj
Sprint | Task Title | Description | Progress
PREP | Download and Install Java JDK and Jenkins | • Install Java JDK 11 or higher • Install Jenkins on local machine or server • Verify Jenkins is running on port 8080 | 100
PREP | Jenkins Configuration | • Install required plugins: - Pipeline Plugin - Git Plugin - GitHub Integration Plugin - Python Plugin • Create Admin User • Configure global security • Manage and Assign Roles | 100
PREP | GitHub Repository Integration | • Connect Jenkins to QuickDoc GitHub repository • Configure webhooks for automatic build triggers • Set up credentials for GitHub access • Test connection | 100
PREP | Environment Setup | • Set up Python 3.x environment • Configure PostgreSQL database connection • Install Docker on Jenkins server • Set up virtual environment for Python dependencies | 100
PREP | Initial Pipeline Setup | • Create Jenkinsfile in repository root • Define basic pipeline stages (Checkout, Build, Test, Deploy) • Configure pipeline for Python Flask/Django application • Test initial pipeline execution | 100
S1 | Configure Python Build Environment | • Install pip dependencies from requirements.txt • Set up virtual environment in pipeline • Configure Flask/Django application settings • Verify Python environment setup | 100
S1 | Implement Automated Testing Stage | • Configure pytest for unit testing • Set up test coverage reporting • Add test results to Jenkins dashboard • Configure test failure notifications | 100
S1 | Database Integration | • Configure PostgreSQL connection in pipeline • Set up database migrations (Flask-Migrate/Django migrations) • Create test database for CI environment • Implement database seed scripts | 100
S1 | Configure Slack Release Notes | • Set up Slack webhook integration for Jenkins • Post release notes to team channel after deployment • Include deployed user stories and crosscuts in notification • Document which features are ready for QA testing | 100
S1 | Validate Team Access to QA Environment | • Create AWS IAM users/roles for all team members • Grant access to QA environment (EC2, S3, RDS) • Test each team member can SSH/access QA server • Document access credentials and procedures for team | 100
S1 | Deploy Build to Dev Environment | • Push code to develop branch • Trigger automated build • Deploy to development server • Verify application is running correctly | 100
S2 | Install Additional Plugins | • HTML Publisher Plugin - for test reports • Email Extension Plugin - for notifications • Docker Pipeline Plugin - for containerization • Credentials Binding Plugin - for secure credentials | 100
S2 | Configure Docker Deployment | • Build Docker image from Dockerfile • Push image to Docker registry • Deploy container to development server • Configure docker-compose for multi-container setup | 100
S2 | Implement Code Quality Checks | • Configure flake8 for Python linting • Set up code coverage thresholds • Add security scanning (bandit for Python) • Generate code quality reports | 100
S2 | TestRigor Integration in Pipeline for QA | • Connect TestRigor API to Jenkins so tests run automatically on QA build | 100
S2 | HTML Test Report Publishing | • Configure HTML Publisher plugin to display pytest results in Jenkins UI | 100
S2 | Configure Notifications | • Set up email notifications for build status • Set up build failure alerts • Configure success/failure notifications to team | 100
S3 | Production Deployment Pipeline | • Configure production environment variables • Set up production database connection • Implement blue-green deployment strategy • Configure production server deployment | 100
S3 | Define Production Credentials | • DATABASE_URL - PostgreSQL connection string • SECRET_KEY - Flask/Django secret key • MAIL_SERVER - Email configuration • PAYMENT_GATEWAY_KEY - Payment integration (if applicable) | 100
S3 | Implement Health Checks | • Add application health check endpoint • Configure Jenkins health monitoring • Set up database connectivity checks • Implement automatic rollback on failure | 100
S3 | Final Pipeline Optimization | • Optimize build times • Implement caching for dependencies • Configure parallel test execution • Document CI/CD pipeline for team | 100