## Road Map
4 | QuickDoc
| Application Modules | Feature Backlog | Story Points | SPRINT 1 | SPRINT 2 | SPRINT 3
|  |  |  | SPRINT1 - 03/24/2026 | SPRINT2 - 04/21/2026 | SPRINT3 - 05/12/2026
| 01. Account Management | 01.01 Register Patient | 3 | X
|  | 01.02 Register Doctor | 3 | X
|  | 01.03 Log In | 3 | X
|  | 01.04 Log Out | 2 | X
|  | 01.05 Modify Profile | 3 | X
01.06 Deactivate Account
|  | 01.07 Show Profile | 2 | X
|  | 01.08 Reset Password | 3 | X
| 02. Doctor Search | 02.01 Search by Specialty | 3 |  | X
|  | 02.02 Search by Location | 3 |  | X
|  | 02.03 Search by Name | 2 |  | X
|  | 02.04 Add to Favorites | 2 |  | X
02.05 Sort by Rating
|  | 02.06 View Doctor Profile | 3 |  | X
| 03. Appointment Booking | 03.01 View Available Slots | 3 |  |  | X
|  | 03.02 Book Appointment | 4 |  |  | X
|  | 03.03 Reschedule Booking | 3 |  |  | X
|  | 03.04 Cancel Booking | 2 |  |  | X
|  | 03.05 View Booking History | 2 |  |  | X
|  | 03.06 Send Booking Reminder | 3 |  |  | X
| 04. Provider Management | 04.01 Add Doctor Profile | 3 |  | X
|  | 04.02 Update Schedule | 3 |  | X
|  | 04.03 Manage Availability | 3 |  |  | X
04.04 View Patient List
04.05 Show Contact Info
04.06 Update Clinic Info
| 05. Reviews & Ratings | 05.01 Submit Review | 3 |  |  | X
|  | 05.02 Rate Doctor | 2 |  | X
|  | 05.03 View Reviews | 3 |  |  | X
05.04 View Review History
05.05 View Rating Summary
| 06. Payment Management | 06.01 Process Payment
06.02 Manage Billing
06.03 Manage Subscriptions
06.04 Process Refund
06.05 View Payment History
| 07. Sales Management | 07.01 Sales Dashboard
07.02 Sales Metrics
07.03 Provider Communication
07.04 Contract Management
| 08. Advertising Management | 08.01 Ads Dashboard
08.02 Create Campaign
08.03 Modify Campaign
08.04 Delete Campaign
08.05 Featured Listings
08.06 View Impressions
08.07 Track Clicks
08.08 Track Conversions
08.09 Ad Revenue Reports
| 09. Medical Records | 09.01 View Medical Records
09.02 View Lab Results
09.03 Request Prescription Refill
09.04 Download Records
| 10. Prescription Management | 10.01 View Prescriptions
10.02 Issue Prescription
10.03 Approve Refill Request
10.04 Deny Refill Request
| 11. Secure Messaging | 11.01 Send Message
11.02 View Inbox
11.03 Message History
11.04 Message Notifications
|  |  | VELOCITY | 19 | 22 | 25

## Jira Road Map S1
Timeline/Roadmap View: Monthly
[Paste your Jira RoadMap screenshot here - expand Epics to show user stories per sprint]
Timeline/Roadmap View: Weekly
Timeline/Roadmap View: Weekly

## Kanban Board
Kanban Board
Sprint 1 - 03/24/2026
Sprint 2 - 04/08/2026
Sprint 3 - 04/29/2026